## Project 2.5 Tasks
PROJECT 2.5 - 7 PERSON TEAM
Person | Role | Task Description | Day | Status | Priority | Notes
Andrew | Project Manager | Restore PrestigeCarsDatabaseScript.sql | Day 1 | Complete | HIGH | Setup database
Andrew | Project Manager | Create Process.WorkflowSteps table | Day 1 | Complete | HIGH | Track all work
Andrew | Project Manager | Create DbSecurity.UserAuthorization table | Day 1 | Complete | HIGH | Add 7 team members
Andrew | Project Manager | Create Utils.uvw_FindColumnDefinition view | Day 2 | Complete | Medium | Metadata tracking
Andrew | Project Manager | Review all team SQL files for consistency | Day 7 | Complete | CRITICAL | Wait for everyone
Andrew | Project Manager | Integrate all SQL into master script | Day 7 | Complete | CRITICAL | Combine all work
Andrew | Project Manager | Create final database backup (.bak) | Day 8 | Complete | CRITICAL | Due for submission
Andrew | Project Manager | Test restore of backup | Day 8 | Complete | HIGH | Verify it works
Andrew | Project Manager | Create PowerPoint (12 slides) | Day 9 | Complete | CRITICAL | After backup done
Andrew | Project Manager | Add voice annotation to PowerPoint | Day 9 | Complete | CRITICAL | 10-12 min total
Haroon |  | Restore database (START NOW!) | Day 1 | Complete | CRITICAL | Everyone blocked!
Haroon |  | Create [Udt] schema | Day 1 | Complete | CRITICAL | Foundation schema
Haroon |  | Analyze columns for UDT needs | Day 1 | Complete | CRITICAL | Plan all types
Haroon |  | Create Udt.SurrogateKeyInt | Day 1 | Complete | CRITICAL | Base type for IDs
Haroon |  | Create text UDTs (CountryName, CustomerName, etc) | Day 1-2 | Complete | CRITICAL | 8 text types
Haroon |  | Create domain UDTs (ISO2, ISO3, Year) | Day 2 | Complete | CRITICAL | Format-specific
Haroon |  | Create numeric UDTs (MoneyAmount, SalesPrice) | Day 2 | Complete | CRITICAL | Currency types
Haroon |  | Create vehicle UDTs (MakeName, StockCode, etc) | Day 2 | Complete | CRITICAL | Auto-specific
Haroon |  | Document UDT hierarchy and reuse | Day 2 | Complete | HIGH | For PowerPoint
Haroon |  | Create SQL script with all UDTs | Day 2 | Complete | CRITICAL | Master UDT file
Haroon |  | SHARE UDT script with team (CHECKPOINT!) | Day 2 | Complete | CRITICAL | Unblock everyone!
zhenkai | Data Modeler | WAIT for Person 2 UDT script | Day 1-2 | complete | Blocked | Cannot start yet
zhenkai | Data Modeler | Run Person 2 UDT script | Day 3 | complete | HIGH | Get UDTs ready
zhenkai | Data Modeler | Backup and DROP Data.Customer | Day 3 | complete | HIGH | Save old data
zhenkai | Data Modeler | CREATE Data.Customer with UDTs | Day 3 | complete | HIGH | New structure
zhenkai | Data Modeler | Add Customer constraints (CHECK, UNIQUE) | Day 3 | complete | HIGH | Data validation
zhenkai | Data Modeler | Add FK: Customer → Country (wait P5!) | Day 4 | complete | HIGH | After P5 Country
zhenkai | Data Modeler | Migrate Customer_OLD data | Day 4 | complete | HIGH | Move all rows
zhenkai | Data Modeler | Backup and DROP Data.Sales | Day 4 | complete | HIGH | Save old data
zhenkai | Data Modeler | CREATE Data.Sales with UDTs | Day 4 | complete | HIGH | New structure
zhenkai | Data Modeler | Add Sales constraints | Day 4 | complete | HIGH | Price, date checks
zhenkai | Data Modeler | Add FK: Sales → Customer | Day 4 | complete | HIGH | Link to customers
zhenkai | Data Modeler | Migrate Sales_OLD data | Day 4 | complete | HIGH | Move all rows
zhenkai | Data Modeler | Create indexes on Sales | Day 5 | complete | HIGH | Performance
zhenkai | Data Modeler | Create SQL script: Person3_Customer_Sales.sql | Day 5 | complete | HIGH | Submit to P1
Azm | Data Modeler | WAIT for Person 2 UDT script | Day 1-2 | Complete | Blocked | Cannot start yet
Azm | Data Modeler | Run Person 2 UDT script | Day 3 | Complete | HIGH | Get UDTs ready
Azm | Data Modeler | Backup and CREATE Data.Make with UDTs | Day 3 | Complete | HIGH | Manufacturers
Azm | Data Modeler | Add Make constraints (CHECK, UNIQUE) | Day 3 | Complete | HIGH | Validation
Azm | Data Modeler | Add FK: Make → Country (wait P5!) | Day 4 | Complete | HIGH | After P5 Country
Azm | Data Modeler | Migrate Make_OLD data | Day 4 | Complete | HIGH | Move all rows
Azm | Data Modeler | Backup and CREATE Data.Model with UDTs | Day 4 | Complete | HIGH | Car models
Azm | Data Modeler | Add Model constraints | Day 4 | Complete | HIGH | Year validation
Azm | Data Modeler | Add FK: Model → Make | Day 4 | Complete | HIGH | Link to makes
Azm | Data Modeler | Migrate Model_OLD data | Day 4 | Complete | HIGH | Move all rows
Azm | Data Modeler | Backup and CREATE Data.Stock with UDTs | Day 5 | Complete | HIGH | Inventory
Azm | Data Modeler | Add Stock constraints | Day 5 | Complete | HIGH | Cost, date checks
Azm | Data Modeler | Add FK: Stock → Model | Day 5 | Complete | HIGH | Link to models
Azm | Data Modeler | Migrate Stock_OLD data | Day 5 | Complete | HIGH | Move all rows
Azm | Data Modeler | Create indexes on Stock | Day 5 | Complete | HIGH | Performance
Azm | Data Modeler | Create SQL script: Person4_Make_Model_Stock.sql | Day 5 | Complete | HIGH | Submit to P1
Kazi | Data Modeler | WAIT for Person 2 UDT script | Day 1-2 | Complete | Blocked | Cannot start yet
Kazi | Data Modeler | Run Person 2 UDT script | Day 3 | Not Started | CRITICAL | HIGH PRIORITY!
Kazi | Data Modeler | Backup Data.Country | Day 3 | Complete | CRITICAL | Save old data
Kazi | Data Modeler | CREATE Data.SalesRegion (NEW TABLE!) | Day 3 | Complete | CRITICAL | Normalize region
Kazi | Data Modeler | Extract unique SalesRegions | Day 3 | Complete | CRITICAL | Get distinct values
Kazi | Data Modeler | DROP old Country, CREATE new with UDTs | Day 3 | Complete | CRITICAL | New structure
Kazi | Data Modeler | Add Country constraints (CHECK ISO codes) | Day 3 | Complete | CRITICAL | Format validation
Kazi | Data Modeler | Add FK: Country → SalesRegion | Day 3 | Complete | CRITICAL | Link regions
Kazi | Data Modeler | Migrate Country_OLD data | Day 3 | Complete | CRITICAL | Move all rows
Kazi | Data Modeler | NOTIFY P3 & P4: Country ready! (CHECKPOINT) | Day 3 | Complete | CRITICAL | Unblock them!
Kazi | Data Modeler | Backup and DROP Data.SalesDetails | Day 4 | Complete | HIGH | Wait for P3&P4
Kazi | Data Modeler | CREATE Data.SalesDetails with UDTs | Day 4 | Complete | HIGH | Transaction details
Kazi | Data Modeler | Add SalesDetails constraints | Day 4 | Complete | HIGH | Price, discount
Kazi | Data Modeler | Add FKs: SalesDetails → Sales & Stock | Day 5 | Complete | HIGH | After P3&P4 done
Kazi | Data Modeler | Migrate SalesDetails_OLD data | Day 5 | Complete | HIGH | Move all rows
Kazi | Data Modeler | Create indexes on SalesDetails | Day 5 | Complete | HIGH | Performance
Kazi | Data Modeler | Create SQL: Person5_Country_SalesDetails.sql | Day 5 | Complete | HIGH | Submit to P1
Mohamed | View Architect | WAIT for P3,4,5 tables complete | Day 1-5 | Complete | Blocked | Need tables first
Mohamed | View Architect | DROP DataTransfer.Sales2015-2018 (4 tables) | Day 6 | Complete | HIGH | Remove old tables
Mohamed | View Architect | CREATE VIEW DataTransfer.Sales2015 | Day 6 | Complete | HIGH | Year filter 2015
Mohamed | View Architect | CREATE VIEW DataTransfer.Sales2016 | Day 6 | Complete | HIGH | Year filter 2016
Mohamed | View Architect | CREATE VIEW DataTransfer.Sales2017 | Day 6 | Complete | HIGH | Year filter 2017
Mohamed | View Architect | CREATE VIEW DataTransfer.Sales2018 | Day 6 | Complete | HIGH | Year filter 2018
Mohamed | View Architect | Test all 4 yearly views | Day 6 | Complete | HIGH | Verify data
Mohamed | View Architect | DROP and CREATE VIEW Output.StockPrices | Day 6 | Complete | HIGH | Calculated view
Mohamed | View Architect | DROP Reference.Budget, Forex, MarketingCat | Day 6 | Complete | HIGH | 3 tables
Mohamed | View Architect | CREATE VIEWs for Budget, Forex, MarketingCat | Day 6 | Complete | HIGH | 3 views
Mohamed | View Architect | DROP Reference.MarketingInfo, SalesBudgets | Day 6 | Complete | HIGH | 2 tables
Mohamed | View Architect | CREATE VIEWs for MarketingInfo, SalesBudgets | Day 6 | Complete | HIGH | 2 views
Mohamed | View Architect | Test all Reference views | Day 6 | Complete | HIGH | Verify data
Mohamed | View Architect | Create SQL script: Person6_Views_Part1.sql | Day 6 | Complete | HIGH | Submit to P1
Ralph | View Architect | WAIT for P3,4,5 tables complete | Day 1-5 | Complete | Blocked | Need tables first
Ralph | View Architect | DROP Reference.SalesCategory, Staff | Day 6 | Complete | HIGH | 2 tables
Ralph | View Architect | CREATE VIEWs for SalesCategory, Staff | Day 6 | Complete | HIGH | 2 views
Ralph | View Architect | DROP Reference.StaffHierarchy, YearlySales | Day 6 | Complete | HIGH | 2 tables
Ralph | View Architect | CREATE VIEWs StaffHierarchy, YearlySales | Day 6 | Complete | HIGH | 2 views
Ralph | View Architect | DROP SourceData.SalesInPounds | Day 6 | Complete | HIGH | 1 table
Ralph | View Architect | CREATE VIEW SourceData.SalesInPounds | Day 6 | Complete | HIGH | 1 view
Ralph | View Architect | DROP SourceData.SalesText | Day 6 | Complete | HIGH | 1 table
Ralph | View Architect | CREATE VIEW SourceData.SalesText | Day 6 | Complete | HIGH | 1 view
Ralph | View Architect | Test all remaining views | Day 6 | Complete | HIGH | Verify data
Ralph | View Architect | Create SQL script: Person7_Views_Part2.sql | Day 6 | Complete | HIGH | Submit to P1